## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2171-swen-261-10-a Team Music
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | RH, 3/14/2022, Passed
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | RH, 3/14/2022, Passed
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | RH, 3/14/2022, Passed
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | RH, 3/14/2022, Passed
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | RH, 3/14/2022, Passed
As a User I want to submit a request to create a customer or admin account (username, password) SO THAT I have an account | GIVEN I submit a user_account object WHEN no account with the given name exists THEN the system should create the account, add it to the list of account, save to the persistent store, and return the account object and a status code of 201 (CREATED) | Pass | AS, 3/14/2022, Passed
| GIVEN I submit a user_account object WHEN an account with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | AS, 3/14/2022, Passed
As a user, I want to be able to purchase all my items through a checkout screen | Given I have items in my shopping cart when I request to make a purchase then I should see a no items left in my cart | Pass | VO, 3/14/2022, Passed
| Given there are items in my shopping cart when I request to make a purchase then those items should decrease in quantity. | Fail | VO, 3/14/2022, Failed; The quantity of the product items cannot be read or updated in the json files in the backend.
As a Customer I want to be able to use a wish list so that i can save products for later purchases | Given I have a product when I select that product and add it to the Wishlist then** the product will enter the Wishlist and return a 200 ok | Pass | DC, 3/14/2022, Passed
| Given I have a product thats already on the wishlist when i select the product to wish list then it will be removed from the wishlist returning a 200 ok | Pass | DC, 3/14/2022, Passed
As a customer want to navigate to the login screenso that I can login and or create an account. | User is able to create an account | Pass | RH, 3/14/2022, Passed
| User is able to login into an account and go to the main page | Pass | RH, 3/14/2022, Passed
| User is able to logout | Pass | RH, 3/14/2022, Passed
As an owner, I want to login to add and remove inventory | Given I am logged as an admin when I navigate to the owner page then I should see a list of products | Pass | AS, 3/14/2022, Passed
| Given I am logged as an admin when I navigate to the owner page then I should be able to delete products | Pass | AS, 3/14/2022, Passed
| Given I am logged in as as admin when I navigate to the owner page then I should be able to update products | Pass | AS, 3/14/2022, Passed
| Given I am logged in as as admin when I navigate to the owner page then I should be able to create products | Pass | AS, 3/14/2022, Passed
| Given I am logged as an admin, I should not be able to see a cart or wishlist as the admin is not a customer. | Pass | AS, 3/14/2022, Passed
As a User, I want to be able to see products in my cart when logged in | Given I am logged in when I navigate to the cart page then I should see a list of products added to my cart. | Pass | RH, 3/14/2022, Passed
As a user I want to be able to search products so that i can have ease of acces to individual products i want. | given a product exits when i look up that product then i should be provided with that product | Pass | SR 3/14/2022, Passed
| givin a product does not exist when i look up that product then i should not be provided with that product | Pass | SR, 3/14/2022, Passed
As a owner I want to be able to have a separate music player product so then I can have specific data to only music player | Given I want to create a music player product when I create the music player product then it should create a MusicPlayerProduct object that is a sub object of Product. | Fail | SR, 3/14/2022, Failed; When testing, there was an issue finding the MusicPlayerDAO and other dependencies.
| Given a product does not exist when i look up that product then i should not be provided with that product | Fail | SR, 3/14/2022, Failed; When testing, there was an issue finding the MusicPlayerDAO and other dependencies.
As a User I want to move my wishlist products to my shopping cart. | **Given** that I move a product **when** I am in the wishlist page ** then** it should be taken to the shopping cart |  |  | PASS | DC, 3/29/2022, Passed
| **Given** that I move a product and the quantity is 0 **when** I am on wishlist, **then** the products stay in the list. |  |  | PASS | DC, 3/29/2022, Passed
As a user I want to view products in my wishlist so that I can buy them another time. | **Given** that I click the wishlist button **when** I am on the website **then** I should be taken to the wishlist |  |  | PASS | DC, 3/29/2022, Passed
As a User, I want to see a homepage so that I know what the store is about | **Given** that I click the home button **when** I am on the website **then** I should be taken to the homepage |  |  | PASS | DC, 3/29/2022, Passed
As a User I want a Products page so that I can view all the Products. | **Given** that I click the products button **when** I am on the website **then** I should be able to view all products |  |  | PASS | DC, 3/29/2022, Passed
As a user I want to navigate to the login page so that I can log into the application. | **Given** that I click the Login button **when** I am on the website **then** I should be taken to the login screen |  |  | PASS | RH, 3/29/2022, Passed
As a user I want to preview a song through a youtube link so that I can see if I want to buy the song. | **Given** I am on the single product page **when** I click the play button on the youtube video **then** I expect to hear the song I am viewing. |  |  | PASS | RH, 3/29/2022, Passed
As a user, I want to see a product page so that I can learn more about a product. | **Given** I am on the product page when** I click the name of the product **then** I should be taken to the product details page. |  |  | PASS | RH, 3/29/2022, Passed
As a User I want a Cart page so that I can view the products I want to buy. | **Given** that I click the cart button **when** I am on the website **then** I should be able to view all products i want to purchase |  |  | PASS | DC, 3/29/2022, Passed
As a user, I want to be able to purchase all my items though a checkout screen and have confirmation of my purchase. | **Given** I have items in my shopping cart **when** I request to make a purchase **then** I should see no more items in my cart |  |  | PASS | VO, 3/29/2022, Passed
| **Given** there are items in my shopping cart **when** I request to make a purchase **then** those items should decrease in quantity. |  |  | PASS | VO, 3/29/2022, Passed
As a User I want a Checkout page so that I can purchase my items | **Given** I have items in my shopping cart **when** I request to make a purchase **then** I should see no more items in my cart |  |  | PASS | VO, 3/29/2022, Passed
As a user, I want to rate a product so that I can let others know what I think about a product. | **Given** that I look at a product **when** I am on the website **then** I should be able to view people's opinions on the product |  |  | PASS | RH, 3/31/2022, Passed
As a developer, I want to account for quantity so that products cannot be purchased when quantity is 0. | **Given** that I have x amount of products in my cart **when** I checkout **then** x amount of the product quantity should be decremented. |  |  | PASS | RH, 3/31/2022, Passed
| **Given** I want to add a product to my cart**when** I try to add more of that product to my cart **then** I should be never able to add more than the product quantity. |  |  | PASS | RH, 3/31/2022, Passed
| **Given** that I want to add a product to my cart **when** that product's quantity is 0 **then** I should not be able to add the product to my cart |  |  | PASS | RH, 3/31/2022, Passed
As a Developer I want to create tests for methods, so I an check that they will perform as expected. | **Given** that I create new tests**when** I create new methods **then** I should have them all pass |  |  | PASS | RH, 3/31/2022, Passed
As a Developer, I want to update the nav bar depending on who is logged in, so that certain privileges aren't accessible to users | **Given** a user is logged in **when** they access the webite **then** they should only be able to see the home, cart, products, wishlist, login, and logout buttons. |  |  | PASS | RH, 3/31/2022, Passed
| **Given** the admin is logged in **when** they access the webite **then** they should only be able to access everything, but the cart and wishlist. |  |  | PASS | RH, 3/31/2022, Passed
As an admin, I want the admin page to look good, so that it is appealing to use | **Given** the admin is logged in **when** they access the webite **then** they should see a admin page styled |  |  | PASS | RH, 3/31/2022, Passed
As an owner, I want to by able to update a product's link and create a product with a link, so that the link field is covered. | **Given** the admin updating a product**when** are on the admin page **then** they should have the option to change the image and video links |  |  | PASS | RH, 3/31/2022, Passed
As a developer, I want the product to have a link field of the image of the product so that I can add the image to the product page | **Given** the user Is looking at a product**when** are on the details page **then** they should have the option to view the image of the song |  |  | PASS | RH, 3/31/2022, Passed
As a developer, I want the product to have a link field of the youtube sample so that I can add the youtube sample to the product page | **Given** the user Is looking at a product**when** are on the details page **then** they should have the option to listen to the song |  |  | PASS | RH, 3/31/2022, Passed